## User Stories
User Stories
US# | Story Category | Title | As a/an… | I want to… | so that… | Priority | Time Estimate
5 | Librarian | Log in | Librarian | Log in to the system | I can access features only available to librarians | 1 | 3
9 | Librarian | Add new materials | Librarian | Add new material to system | I can updated the current inventory database | 2 | 5
7 | Librarian | Record a Check in item | Librarian | Record a Check in item | I can move a item from check out database to inventory database | 3 | 5
6 | Librarian | Record a Check out item | Librarian | Record a Check out item | I can keep an record when a patron check out material in the system | 4 | 3
12 | Patron | Patron checkout | Member | Checkout Materials | I can loan materials from the library for personal use. I can loan materials from the library for a maximum period of 30 days. If I exceed 30 days I will be fined $0.10 per day per overdue item. | 4 | 3
10 | Librarian | Search the system | Librarian | Search material in the system | I can view the current status of the material: check out/in; hold by which patron; due date; | 6 | 1
11 | Librarian | Manage partons' membership | Librarian | Manage partrons' membership | I can CRUD patron's membership and informations. | 7 | 5
22 | User | Search Materials | User | Search materils | I can search materials by: (1) MaterialID and/or (2) Title and/or (3) Author and/or (4) Subject. I can then view search results and view whether the material is avaible | 8 | 2
27 | System | Daily Report Generation | System | Generate Daily Report | it will send an e-mail to member who has to return a item in 5 days; it will calculate fines for each overdue item automatively; it will send an e-mail to members on their first overdue day | 9 | 5
8 | Librarian | Manage Fines | Librarian | Receive fines from past due patrons | the patrons will clear the past due record and continue to be regular member | 11 | 1
23 | User | Library Contract | User | see the library email and phone number | I can contact the library with questions aor concerns | 13 | 1
24 | User | Library Hours | User | see when the library will open | I know when I can visit | 14 | 1
25 | User | Library Map | User | see a map of the library location | I can find the library | 15 | 2
26 | User | Mobile accessbility | User | use all users' function in my mobile |  | 16 | 4
20 | Patron | Log in | Member | Log in the system | I can search material, add material to wishlist, make material reservations | 20 | 1
13 | Patron | Change personal information | Member | change my password and contract information | I can make sure my address and contact information is current; account is secure by changing password | 21 | 1
15 | Patron | View mateirals record | Member | View my loan record and view any accrued fines | I can view my material loan history. I can view what materials I checkout in the past. I can view when any currently loan materials are due. I can view if I have any fines. I can view if I have any reserved matierials. I can only view my own record - I will have to authenticate i.e. Login | 23 | 3
18 | Patron | Search Materials -Patron | Member | Search Materials | I can search materials by: (1) MaterialID and/or (2) Title and/or (3) Author and/or (4) Subject. I can then view search results | 24 | 2
17 | Patron | Reserve Materials | Member | Reserve Materials | I can reserve materials that are currently checked out, but that I wish to checkout in the future. I cannot reserve materials that are currently checked in. When a reserved material is returned to the library I will be notified if I am next in queue | 25 | 5
16 | Patron | Pay fines | Member | Pay fines | I can pay fines to stay in good standing with the library and continue to loan materials | 26 | 1
14 | Patron | Receive info when reserved item is availble | Member | Receive info when reserved item is availble | when the wanted item is returned, I will ne notified and can check it out | 27 | 1
19 | Patron | CRUD Wishlist | Member | CRUD Wishlist | I can add and delete items from my wishlist. My wishlist will show the status of the material(wether it is cheked in or out). My wishlist will indicate if I have checked out an iteam before. I can view my wishlist on a mobile device. | 28 | 4
2 | Super Librarian | Log in | Super Librarian | Log in to the system | I can access features only available to super librarians | 31 | 1
3 | Super Librarian | Create/Read/Update/Delete patron | Super Librarian | CRUD patrons' information | I can updated the current patron database | 32 | 1
4 | Super Librarian | CRUD Librarian emplyoment | Super Librarian | Manage librarian emplyoment | I can control the employment of employees database | 33 | 1
1 | super Librarian | Manage website | Super Librarian | Update hours and contact information on the website | I can keep the information current for users to access | 34 | 1
21 | User | guest can apply for membership | User | Apply for Membership | I can apply to be a member of the library. If made a member I will receive a library card with which to checkout materials | 40 | 1
28 | System | Internal Audit | System | Perform interal audit | a member will not allowed to check out other items if they have already check out 5 items; a member will not alowed to check out other items if they have unpaid overdue; | 50 | 3
29 | System | Manage wishlist | System | Manage wishlist | It will generate a wishlist report weekly to see the partons demand; | 51 | 2
[6 empty] | Person-hours of work: | 69
[6 empty] | Assuming 70% velocity, the hours it will take to actually complete the work: | 98.5714
We will take 3 weeks for each iteraion, each member contributes 4 hours per week and we have 4 members in our team. In this situation, the total work hours for each iteration is 48 hours.
[5 empty] | Hours of work (including 70% velocity) that can be completed by a 4 person team in 1 iteration: |  | 48
[5 empty] | How many iteraion we will have : |  | 2.0536
The different iterations are painted into different colors.

## Dictionary
SLPL Information System Dictionary
| Term | Definition
1 | Non-member Patron | Patron who can only search in the library, but can not check out a item
2 | Member Patron | Patron who can seach in the library, check out/return/reserve a item, CRUD wishlist
3 | Librarian | Library staffs who help patron check out/return item
4 | Super Librarian | Library adminstrators who manages account and information of both patrons and librarians
5 | System | A automatic information that can gengerate report by a certain time basis
6
7
8
9
10
11

## Business Rules
SLPL Information System Business Rules
| BR-1 | Only librarians are allowed to add, modify, and delete materials in the materials database.
| BR-2 | No-members should be able to search materials by author and title without being required to login.
| BR-3 | If a member has a past due on record, he can not check out more books
| BR-04 | A member can only hold 5 items in the system, he can not check out items if he already check out 5 items.
BR-03

## Technical Requirements
SLPL Information System Technical Requirements
* Indicates the BR will not be implemented for this project, but serves as an example for future projects.
| TR-1 | The system shall fully operate with current versions of Microsoft Internet Explorer, Firefox, and Google Chrome as well as standard Android and IOS browsers.
| TR-2 | The system shall fully operate on a corporate approved, Microsoft Windows 200? server using Internet Information Server ?. (instruct.biz.uiowa.edu)
| * TR-3 | The system shall accommodate 100 concurrent users at peak usage times of 9AM – 4PM, local time.
| * TR-4 | All pages generated by the system shall be fully downloadable in no more than 10 seconds over a 512kbsp DSL connection.
| TR-5 | Responses to queries shall take no longer than 7 seconds to load onto the screen after the users submits the query.

## Constraints
SLPL Information System Constraints
* Indicates the CO will not be implemented for this project, but serves as an example for future projects.
| * CO-1 | All network transactions that involve logins, financial information, or personally identifiable information shall be encrypted.
| * CO-2 | The system shall provide an online hierarchical cross-linked help system in HTML that describes, illustrates, and provides examples for all system functions.
| CO-3 | All HTML code shall conform to XHTML 1.0 transitional.
| CO-4 | All CSS code shall conform to CSS 2.1.